## Fieldwork_Journal
AIGGPA FIELDWORK JOURNAL — Aryan Kori (Research Intern)
Assessment of Digital Tool Adoption & Impact on Efficiency in MP Government Departments
Date | Location | Department | Activity | Respondents Collected | Evidence Source | Notes / Observations
2026-05-04 | Bhopal — AIGGPA Office | All | Research Infrastructure Setup | — | Vault file timestamps | Created AIGGPA Fieldwork Vault — full directory structure, Master Tracker (7 sheets), observation checklist template, consent form template, setup_respondent.py, validate_tracker.py, transcribe_audio.py. Data management infrastructure fully operational.
2026-05-05 | Bhopal — AIGGPA Office | All | Instrument Finalisation & Pilot Planning | — | Project files | Finalised 88-question survey schedule across 4 departments. Built department-specific question blocks (Q60–Q81). Prepared Hindi/English bilingual versions. Printed hardcopies for Forest HQ pilot.
2026-05-12 | Bhopal — AIGGPA Office / Coordination | Forest | Permission & Coordination | — | WhatsApp group / institutional process | Initiated formal permission routing for Forest Department HQ access. Coordinated with PCCF office for schedule of officer availability. Prepared respondent shortlist from official MP Forest web teledirectory.
2026-05-13 | Bhopal — MP Forest HQ (Satpura Bhawan / Van Bhawan) | Forest | Pilot Data Collection — Day 1 | 8–10 | Forest report metadata (May 2026) | Commenced Forest HQ pilot. Surveyed senior Class I officers (IFS cadre) — PCCF office, APCCF offices. Collected consent forms. Validated instrument with Class I respondents — confirmed all 88 questions functional.
2026-05-14 | Bhopal — MP Forest HQ (Satpura Bhawan) | Forest | Data Collection — Day 2 | 8–10 | Forest report metadata | Continued Forest HQ fieldwork. Focused on Class II (अधीक्षक / Superintendents, सहायक वन संरक्षक / ACFs) across sections: प्रशासन, समन्वय, मानव संसाधन विकास, सतर्कता एवं शिकायत. Observed e-Office usage at workstations.
2026-05-15 | Bhopal — MP Forest HQ (Satpura Bhawan) | Forest | Data Collection — Day 3 | 8–10 | Forest report metadata | Surveyed Class III staff (निज सहायक, लेखपाल, शीघ्रलेखक, मानचित्रकार) from वित्त/बजट, सूचना प्रोद्योगिकी, भू-अभिलेख, उत्पादन sections. Key observation: Class III uses e-Office daily but reports moderate UI difficulty.
2026-05-18 | Bhopal — MP Forest HQ (Satpura Bhawan) | Forest | Data Collection — Day 4 | 10–12 | Forest report metadata | Completed Class IV respondents (सहायक ग्रेड-3, स्टेनोटाइपिस्ट, वनरक्षक). Critical finding: Class IV confidence = 1/5, difficulty = 5/5, yet PU = 4/5. 70% report no department GPS device. Completed Forest HQ — N=40 achieved.
2026-05-19 | Bhopal — AIGGPA Office | Forest | Data Entry & Initial Coding | — | Project files | Entered all 40 Forest HQ responses into master spreadsheet. Began TAM/UTAUT emergent coding. Identified 14 construct codes. Built cross-tabulation framework (Training × Internet × PU).
2026-05-20 | Bhopal — AIGGPA Office | Forest / All | Analysis Framework Development | — | Research Framework file | Built complete Research Framework: TAM-UTAUT Coding Matrix, Cross-Tab Analysis, RD Hypotheses Tracker (H1–H5), Interview Probes (bilingual), Policy Blueprint (R1–R5). Framework designed for replication across remaining 3 departments.
2026-05-26 | Bhopal — M.P.F.D. Khel Parisar / Divisional Forest Office | Forest | District Office Pilot + Observation | ~5 | WhatsApp group message | Visited Divisional Forest Office at Khel Parisar for Forest DO data collection. Began District Office pilot — surveyed field-level staff. Could not attend 3:30 PM office meeting due to ongoing fieldwork.
2026-05-27 | Field — Forest Division / District Offices | Forest | District Office Data Collection | ~5–7 | Respondent count estimate | Continued Forest DO fieldwork. Targeted Range Officers and field staff at district level.
2026-06-02 | Bhopal — Vikas Bhawan (RD HQ) / Field coordination | Rural Development | RD Data Collection Launch — Day 1 | 13 | Field survey schedules | Launched Rural Development data collection at Vikas Bhawan. Surveyed 13 SRLM staff (Block Managers, District Managers, ABMs, and Samta Samnvyek staff) using the digital tool adoption questionnaire. Respondents include Ghanshyam Yadav, Sunita Chandne, Dr. Akhilesh Kumar Singh, Shahana Khan, Nisha Padwar, etc.
2026-06-03 | Bhopal — Vikas Bhawan / Field | Rural Development | RD Data Collection — Day 2 | 5 | Field survey schedules | Continued RD digital adoption data collection. Surveyed 5 additional respondents: Suresh Kumar Prajapati (Block Manager), Anamika Patil (Samta Samnvyek), Sarswati Hanote (Samta Sakhi), Laxmi Rajak (BM), Manoj Kumar Maurya (DFM).
2026-06-04 | Bhopal — Coordination / Remote | Rural Development | RD Follow-up Collection | 1 | Field survey schedules | Completed follow-up RD survey collection. Received response from Nemchand Jadav (Asst. State Project Manager). Total RD respondents collected: 19.
2026-06-07 | Bhopal — Home / AIGGPA Office | All | Data Integration & Meeting Preparation | — | Vault integration pipeline | Ingested all 40 Forest respondents into Master Tracker. Updated Sampling Dashboard. Exported filtered RD data (19 respondents). Built data entry workbook. Prepared analysis framework and presentation materials for Monday review meeting.
CUMULATIVE TOTAL |  |  |  | ~74 | Forest HQ=40 + Forest DO≈12 + RD≈19 + Prior≈3
LEGEND:
■ Green = Forest Dept |  | ■ Orange = Rural Development |  | ■ Blue = All / Admin