# Background

The Government of Madhya Pradesh, architected primarily by technical agencies such as MAP-IT and NIC, has built an impressive portfolio of digital platforms across its key departments:

- School Education: Education Portal 3.0 is designed to manage approximately 350,000 permanent teachers.

- Health: The department operates HRMIS, NHM CHETNA, and Ayushman Sakhi.

- Forest: Uses satellite data for encroachment alerts and wildlife tourism permitting.

Institutional observation reveals a design-reality gap where day-to-day workflows still default to physical registers and informal digital tools.

# Rationale

Maximizing the adoption of IT tools translates to productivity gains and structural resilience. Modernization bridges the talent drain by automating manual workarounds historically rigid in routine processing.

# Capacity Building Framework

Mission Karmayogi shifts from rule-based to role-based competency. This research feeds AIGGPA’s mandate to design evidence-based modules for the iGOT platform.

# Theoretical Framework

This study employs the Unified Theory of Acceptance and Use of Technology (UTAUT), mapping Performance Expectancy (PE), Effort Expectancy (EE), Social Influence (SI), and Facilitating Conditions (FC).

# Research Objectives

- Map actual tool usage across official categories.

- Assess document workflow and record maintenance.

- Capture the IT department’s perspective via login statistics.

- Classify barriers using the UTAUT framework.

- Produce actionable recommendations for AIGGPA training design.

# Scope

- Departments: School Education, Health, Forest (Madhya Pradesh).

- Respondents: Class I, II, III officials and IT staff.

- Duration: April to June 2026 (10 weeks).

# Methodology

This mixed-methods study uses two parallel streams:

- Stream A: Tasks, tools, portals, and training history.

- Stream B: Platform deployment stats and IT support structure.

## Sampling Strategy

Purposive sampling of 54 respondents analyzed as stratified case studies.

## Data Collection Instruments

1. Semi-structured interview guide. 2. Aggregated usage statistics (IT nodal data). 3. Direct workflow observation checklist.

## Data Analysis Plan

Manual thematic coding using ATLAS.ti, following Braun & Clarke (2006). Discrepancies between qualitative claims and numerical metrics isolate hidden blockers.

# Work Plan

A 10-week schedule covering literature review, pilot testing, departmental observations (Weeks 4-8), and final report generation (Week 10).

# Budget Estimate

Total Research Budget: 30,000 INR (covering transit, software licensing, and consumables).

# Limitations and Ethical Considerations

Covers access constraints, self-reporting bias, and the Hawthorne effect (mitigated via IT Ecosystem Audit). Ethical standards ensure voluntary participation and data anonymity.

# Expected Output

# References

Venkatesh, V., et al. (2003). User acceptance of information technology: Toward a unified view. MIS Quarterly. Heeks, R. (2003). Most IT-for-development projects fail. Braun, V., & Clarke, V. (2006). Using thematic analysis in psychology.